## Sheet2
Category | Category COPY for Client Topic | Smolders ID | Sobject | Commercial improvement / topic | Smolders Category | Contact person | When to be discossed | Impact cost (indicative) | impact planning | Standard Smolders way | ref. Tenderer procedore | Clarification / risk | New standard to be | Comments
Welding | Welding | TEG9 | PWHT | PWHT is ommited by the use of FM file EN 1090 No requirements per standard for standard Carbon steel DNV standards: DNV-OS-C101: Special areas with material thickness >50mm DNV-OS-ST-0126 Steel ≥420MPa, Special areas, thickness >50mm | Gold | Technology-department | If in ER-Not for Serial projects | If Employer doesn’t allow ommitance of PWHT: New WPQR to be welded Butt weld test piece (thickness: +/-50mm): €5600 + extra cost for PWHT Fillet weld test piece (thickness: +/-30mm): €2300 + extra cost for PWHT Extra cost + time for production as PWHTs are to be given in production: New type of consumables to be used (more expensive + risk on mistakes in production) Should always be excluded because is not possible to put cost on. One off -> hr/ ton possible to be calculated case by case | If employer doesn't allow for PWHT to be omitted this means following to be taken into account: - increase in lead time for production ==> +/- 1 day to perform PWHT of the weld | Fracture mechanics file with CTOD testing will be provided if required through standard All weld connections prone to prone to PWHT as per Standards will be covered with fracture mechanics file covered by CTOD test qualifications Base material is covered based on weldability reports of Material supplier Weld is coverd with tests welded by Smulders For these connections extra precautions are taken in production. | N/A | see impact on cost/planning | N/A | If in ER-Not for Serial projects,If Employer doesn’t allow ommitance of PWHT: New WPQR to be welded Butt weld test piece (thickness: +/-50mm): €5600 + extra cost for PWHT Fillet weld test piece (thickness: +/-30mm): €2300 + extra cost for PWHT Extra cost + time for production as PWHTs are to be given in production: New type of consumables to be used (more expensive + risk on mistakes in production) Should always be excluded because is not possible to put cost on. One off -> hr/ ton possible to be calculated case by case ,N/A,If employer doesn't allow for PWHT to be omitted this means following to be taken into account: - increase in lead time for production ==> +/- 1 day to perform PWHT of the weld,Fracture mechanics file with CTOD testing will be provided if required through standard All weld connections prone to prone to PWHT as per Standards will be covered with fracture mechanics file covered by CTOD test qualifications Base material is covered based on weldability reports of Material supplier Weld is coverd with tests welded by Smulders For these connections extra precautions are taken in production.,N/A,see impact on cost/planning
T&I | T&I | TEG8 | Sea fastening | No deviation from assumptions, Depending on MWS often following standard: DNVGL-ST-N001, Fabrication according EN 1090-2 or DNV-OS-C401 | Gold | Engineering-department | If in ER- For One Off projects | Changes in requirements:, Possible that no re-use is possible, Extra fabrication works, Cost /kg increases., Note: Re-use existing grillages could contribute to cost reduction | Changes in requirements:, Possible that no re-use is possible Extra fabrication works | To standard, During tender assumptions made to calculate price to be included in contract, Material grade, Fabrication standard, NDT-scope, Transport conditions | N/A | See impact cost/planning | N/A | If in ER- For One Off projects,Changes in requirements:, Possible that no re-use is possible, Extra fabrication works, Cost /kg increases., Note: Re-use existing grillages could contribute to cost reduction,N/A,Changes in requirements:, Possible that no re-use is possible Extra fabrication works,To standard, During tender assumptions made to calculate price to be included in contract, Material grade, Fabrication standard, NDT-scope, Transport conditions,N/A,See impact cost/planning
Technology | Technology | TEG7 | General | Access on SMU yards !Smulders code of conduct) has to be signed by client rep. And, therefore to be included in the contract. | Gold | Production managers Sites | If contract minded client ==> to be, discussed with Project director. |  |  |  | P-HSM-GR-048 Code of conduct for client, representatives | As all sites request Client reps. to sign this statement, however often not in line with ER. |  | If contract minded client ==> to be, discussed with Project director.,P-HSM-GR-048 Code of conduct for client, representatives,As all sites request Client reps. to sign this statement, however often not in line with ER.
Project set-up | Project set-up | TEG6 | Material | Design T < -10°C for DNV design not to be accepted For BSH design <-15°C as reference temperature to be discussed. | Gold | Technology /Engineering | If in ER | Possibly new WPQR/CTODs to be welded and exta tests to be, performed on material, to be determined on a case by case, Cost WPQRs: FW: 2000€ / test FP: 5000€/test, CTOD: 20000€/test, Case by case calculation to be made based depending on scope | possible impact on availability of material | For DNV projects design T at -10°C For BSH projects ref. T at -15°C | N/A | When lower design T / ref. T is specified this has influence, on which materials are allowed with possible risk on CVN, values at -60°C / CTOD tests to be performed at T <-10°C .. | N/A | If in ER,Possibly new WPQR/CTODs to be welded and exta tests to be, performed on material, to be determined on a case by case, Cost WPQRs: FW: 2000€ / test FP: 5000€/test, CTOD: 20000€/test, Case by case calculation to be made based depending on scope,N/A,possible impact on availability of material,For DNV projects design T at -10°C For BSH projects ref. T at -15°C,N/A,When lower design T / ref. T is specified this has influence, on which materials are allowed with possible risk on CVN, values at -60°C / CTOD tests to be performed at T <-10°C ..
Project set-up | Project set-up | TEG4 | Design | Design of welded connections FP vs Full strenght | Gold | Technology ? Engineering | Always ! If design in SMU Scope), Only for static loaded components ! not, for fatigue loaded items) | Project specific to be checked following possible impact:, - Welding hours, - NDT scope, Cost saving: To be evaluated in value engineering case by case/, Engineering: Additional costs to be taken into account. | Project specific to be checked, following possible impact:, - Dimensional control, - Fit-up, -Welding hours, - NDT scope !limited access) | Depending on structural category: FP to be avoided as much as possible. | N/A | see impact cost/planning | N/A | Always ! If design in SMU Scope), Only for static loaded components ! not, for fatigue loaded items),Project specific to be checked following possible impact:, - Welding hours, - NDT scope, Cost saving: To be evaluated in value engineering case by case/, Engineering: Additional costs to be taken into account.,N/A,Project specific to be checked, following possible impact:, - Dimensional control, - Fit-up, -Welding hours, - NDT scope !limited access),Depending on structural category: FP to be avoided as much as possible.,N/A,see impact cost/planning
NDT | NDT | TEG3 | NDT Crosscheck | Crosschecking of NDT by Employer can be accepted if following cases can be agreed:, Always in presence of Smulders Level 3, Testing will be performed following project NDT procedures and same, equipment/calibration/reference blocks., Testing will not have an influence on the production flow !e.g. It is not acceptable to have crosschecks performed in blast shop)., Cost is to be borne by Employer | Gold | Technology-department | If in ER | Extra cost for making people available | Impact on planning !possible delays on, bottlenecks), Impact on other projects. | N/A | N/A | See impact cost/planning, possible discussions during the project execution if, crosschecks are performed not in line with how NDT is, performed by Smulders. | N/A | If in ER,Extra cost for making people available,N/A,Impact on planning !possible delays on, bottlenecks), Impact on other projects.,N/A,N/A,See impact cost/planning, possible discussions during the project execution if, crosschecks are performed not in line with how NDT is, performed by Smulders.
Fab & QC | Fab & QC | TEG2 | Tolerances flanges | Fabrication tolerances for Flanges of TPs ==> always to be discussed with planned, fabrications location., No acceptance on tolerances without approval of planned fabrication sites. | Gold | Technology-department | When tolerances deviating from standard SMU procedure | Possibly milling of flanges to be included in the pricing. Fixed cost, for renting machining tool, 750K, one tool should be sufficient to, machine up to 3 TPs per week, 2 flanges per TP considered, Machining cost 15K each flange., Above cost apply for a serial TP project where all flanges are to be machined,, Cost for machining of only 1 or 2 TPs. in a serial project where the, flange is out of tolerance are around 25k-30K per flange. | possible impact due to need of milling. | No specific values depending on sizes of flanges and design around flange. | N/A | see impact cost/planning | N/A | When tolerances deviating from standard SMU procedure,Possibly milling of flanges to be included in the pricing. Fixed cost, for renting machining tool, 750K, one tool should be sufficient to, machine up to 3 TPs per week, 2 flanges per TP considered, Machining cost 15K each flange., Above cost apply for a serial TP project where all flanges are to be machined,, Cost for machining of only 1 or 2 TPs. in a serial project where the, flange is out of tolerance are around 25k-30K per flange.,N/A,possible impact due to need of milling.,No specific values depending on sizes of flanges and design around flange.,N/A,see impact cost/planning
Welding | Welding | TEG11 | Crack Tip Open Displacement (CTOD) test criteria | Test criteria for CTOD testing more stringent than:, Test temperature <-10°C, CTOD value >0,15 !to be checked 0,25 can be possible). | Gold | Technology-department | If in ER | If CTOD is required with more stringent requirements than given in, column C ==> extra CTOD tests will need to be performed:, CTOD tests are more expensive than normal weld tests, +/- €20.000 per test piece, Total amount of the new PQR's and amount of new CTOD tests, shall be evaluated case by case based on the project scope. |  | Fracture mechanics file with CTOD testing will be provided if required through standard, All weld connections prone to FM will be covered with CTOD test qualifications, Base material is covered based on weldability reports of Material supplier, Weld is covered with tests welded by Smulders, For these connections extra precautions are taken in production., Based on test temperature -10°C and value of 0,15 | N/A | Possible high extra cost and time for extra qualifications., These test are also not available for base material, so amount of extra tests could be very extensive | N/A | If in ER,If CTOD is required with more stringent requirements than given in, column C ==> extra CTOD tests will need to be performed:, CTOD tests are more expensive than normal weld tests, +/- €20.000 per test piece, Total amount of the new PQR's and amount of new CTOD tests, shall be evaluated case by case based on the project scope.,N/A,Fracture mechanics file with CTOD testing will be provided if required through standard, All weld connections prone to FM will be covered with CTOD test qualifications, Base material is covered based on weldability reports of Material supplier, Weld is covered with tests welded by Smulders, For these connections extra precautions are taken in production., Based on test temperature -10°C and value of 0,15,N/A,Possible high extra cost and time for extra qualifications., These test are also not available for base material, so amount of extra tests could be very extensive
Welding | Welding | TEG10 | Crack Tip Open Displacement (CTOD) and Post Weld Heat Treatment (PWHT) | CTOD is a specific test to determine thoughness of a welded connection., Fabrication according EN 1090-2 !Design according Eurocode) ==> no CTOD applicable as, this is not included in Euro code and/or EN1090-2 standard, Design / fabrication according DNV-OS-C401 ==> CTOD possibly neccesary due to:, Ommiting of PWHT if required through fabrication/design standard, Increase of impact test temperature to -40°C instead of -60°C, Required for design standard: special area / design T <10°C / one of the members, SMYS>420MPa, Engineering critical analysis is always to be excluded from contract price | Gold | Technology-department | If in ER | If CTOD is required for other connections than those prone to FM, analysis due to requirements of the standard ==> extra tests are to, be welded., CTOD tests are more expensive than normal weld tests, +/- €20.000 per test piece, Engineering critical analysis is always to be excluded from contract price (specific attention if DNV & Lloyds' have a part in the, contract, costimpact of ± 50 000€), ECA for Jacket +/-55K€ for a topside +/-20K€, Extra engineering hours, Possible changes necessary to design, Extra weld test to be made, ..., This can only be done once a design is available! !critical, connections, thicknesses, materials,...) | N/A | Fracture mechanics file with CTOD testing will be provided if required through standard, All weld connections prone to FM will be covered with CTOD test qualifications, Base material is covered based on weldability reports of Material supplier, Weld is coverd with tests welded by Smulders, For these connections extra precautions are taken in production. | N/A | see impact on cost, When performing an engineering critical analysis, it could, show dissimilarities with the design, verification ongoing, with DNV by engineering department | N/A | If in ER,If CTOD is required for other connections than those prone to FM, analysis due to requirements of the standard ==> extra tests are to, be welded., CTOD tests are more expensive than normal weld tests, +/- €20.000 per test piece, Engineering critical analysis is always to be excluded from contract price (specific attention if DNV & Lloyds' have a part in the, contract, costimpact of ± 50 000€), ECA for Jacket +/-55K€ for a topside +/-20K€, Extra engineering hours, Possible changes necessary to design, Extra weld test to be made, ..., This can only be done once a design is available! !critical, connections, thicknesses, materials,...),N/A,N/A,Fracture mechanics file with CTOD testing will be provided if required through standard, All weld connections prone to FM will be covered with CTOD test qualifications, Base material is covered based on weldability reports of Material supplier, Weld is coverd with tests welded by Smulders, For these connections extra precautions are taken in production.,N/A,see impact on cost, When performing an engineering critical analysis, it could, show dissimilarities with the design, verification ongoing, with DNV by engineering department
Welding | Welding | TEG5 | Artic material | If DIN 18088-3 is specified, to assure artic material is not specified and/or design should be, above -10° | Gold | Technology/Engineering | If in ER | cost/availability: cost of material + cost for extra WPQR and, possible CTOD tests | yes ==> new WPQR/CTOD/No-stock, material - delivery | no artic steels | N/A |  |  | If in ER,cost/availability: cost of material + cost for extra WPQR and, possible CTOD tests,yes ==> new WPQR/CTOD/No-stock, material - delivery,no artic steels,N/A
Fab & QC | Fab & QC | TEG1 | Inspections: notification period | Agreements notifications periods to be agreed up front and to be in line with Smulders way of working. !ref to statement). | Gold | Production managers sites, QA managers sitess, Technology | When more stringent requirement mentioned in ER | To be checked project specific | To be checked project specific | Internal in-process inspection !DC, NDT, release between Smulders yards,...), Will be performed by SMU-personnel and can be monitored by Employer, however no specific notification will be issued., 2-weekly look-a-head for some inspections !general what is ongoing) Informal confirmation can be given trough (e.g. a what's app group), Final inspections 2-weekly look-a-head with planning, Confirmation of date will be given 48-hours in advance On day of inspection possible change in exact timing !up to 8 hrs depending on repair etc), For bottleneck activities such as blasting, a Hold Point is not allowed !Witness point) |  | If employer can't agree following options can be given:, Full-time employer inspector!s) available on fabrication sites, where employer wants to witness in-process inspections., Acceptance of delay in planning/shift of LD dates, due to, possible stops because SMU has to wait for employer, inspectors. !only possible if no effect on other projects), Surveillance of the production by a 3rd party which will, perform spotchecks on in-process inspections. | N/A | When more stringent requirement mentioned in ER,To be checked project specific,N/A,To be checked project specific,Internal in-process inspection !DC, NDT, release between Smulders yards,...), Will be performed by SMU-personnel and can be monitored by Employer, however no specific notification will be issued., 2-weekly look-a-head for some inspections !general what is ongoing) Informal confirmation can be given trough (e.g. a what's app group), Final inspections 2-weekly look-a-head with planning, Confirmation of date will be given 48-hours in advance On day of inspection possible change in exact timing !up to 8 hrs depending on repair etc), For bottleneck activities such as blasting, a Hold Point is not allowed !Witness point),If employer can't agree following options can be given:, Full-time employer inspector!s) available on fabrication sites, where employer wants to witness in-process inspections., Acceptance of delay in planning/shift of LD dates, due to, possible stops because SMU has to wait for employer, inspectors. !only possible if no effect on other projects), Surveillance of the production by a 3rd party which will, perform spotchecks on in-process inspections.
Coating | Coating | CG3 | Guarantee agreement with IP | Deviation from Guarantee conditions between IP and Tenderer standard agreements | Gold | Coating Surface Treatment Department | Everytime |  |  |  |  | Possible higher risk on liability for coating repair works, offshore during DNP period.Possibily extended DNP period |  | Everytime,Possible higher risk on liability for coating repair works, offshore during DNP period.Possibily extended DNP period
Coating | Coating | CG2 | Cleaning / Fly rust contamination | - The contract shall include arrangements with regard to Fly rust., - Preventive measures shall be taken during cutting, welding and grinding in the yards., - The entire surface of all WTG foundations shall be cleaned prior to Take-over by means of, high- pressure water cleaning with warm tap water or demineralized water, - An option will be included in the Contract for additional cleaning services / The contract, shall include a contract option for additional cleaning of WTG foundations / Fixed unit rates, for CTV will be included in the contract, - Contractor shall not accept any reservations on the take-over certificate with regard to fly, rust., - Superficial fly rust shall not be considered a coating defect | Gold | Coating Surface Treatment Department | Always-to be part of contract. ! check with Tender Dept.) | If cleaning is requred 2000 Euro/Foundation. One Off to be, checked case by case | See statement | See statement on Fly rust:, Following to be included in contract regarding fly-rust, Agreements on preventive measures to be taken !cost to be taken into account), How to clean at take-over !cost to be taken into account), Option for additional cleaning !cost to be borne by employer), Contractor shall not accept any reservations on the take-over certificate with regard to fly rust Superficial fly rust shall not be considered a coating defect. | loose statement covering cleaning and fly rust | see statement | N/A | Always-to be part of contract. ! check with Tender Dept.),If cleaning is requred 2000 Euro/Foundation. One Off to be, checked case by case,N/A,See statement,See statement on Fly rust:, Following to be included in contract regarding fly-rust, Agreements on preventive measures to be taken !cost to be taken into account), How to clean at take-over !cost to be taken into account), Option for additional cleaning !cost to be borne by employer), Contractor shall not accept any reservations on the take-over certificate with regard to fly rust Superficial fly rust shall not be considered a coating defect.,loose statement covering cleaning and fly rust,see statement
Coating | Coating | CG1 | Holiday Testing | manufacturers recommendations.This should be discussed and the Holiday test statement should be added to the tender review comments for discussion. Tendererlders has a Hoilday test procedure .This test procedure is in line with our paint | Gold | Coating Surface Treatment Department | At Tender Review Stage | Planning for storage, Planning for testing, Planning and time and product for repairs., To be checked case by case | Yes ,Holiday testing is time consuming, and will have to be planned into the, schedule | Holiday Test Statement, In certain protective coatings systems, it is important to test the finished coating system for flaws and/or pinholes as these defects can lead to premature, coatings failure in service., This is particularly important if the structure is Primary steel or if it will be used in an immersed or semi-immersed situation. Secondary steel is not, generally holiday tested., It is not reccomended to carry out HV holiday testing over TSZA. Our experience shows DFT's of the metallization generally have a wide variation from, NDFT to several hundred pm., In some spots this may result in a high DFT of metallization and low DFT of coating system. Whilst the total DFT may meet the specification, the low DFT of, coating system in such spots may result in damages to coating and impact accuracy of holiday testing., Testing, The suggested frequency for testing shall be 5% of the total coated surface. The location of the 5% shall be agreed by Tendererlders and the Client Representative prior to testing., A Maximum of 5 findings per 100 m2 of the tested surface are acceptable. A finding is defined as a spot of max. 0,1 m2 with one or various detected pores., In case of more findings and/or one of the spots exceeds the max. size, the next level of testing has to be applied., In case of more then 5 findings per 100 m2 tested surface, additional +10% surface is measured. . If no further pinholes are detected, the coated surface is, accepted. If additional pinholes are detected, the entire coated surface is checked., All findings have to be repaired according the agreed repair procedure., A retest of the repaired spots will not be performed. It is not reccomended by the paint manufacturer and holiday testing the same area more than once, could lead to the unnecessary damages of already Sound coatings., Principle, Porosity in a protective paint system applied to a conductive metal surface is detected either by low-voltage wet-sponge testing or high-voltage spark, testing., Low-voltage pinhole detectors use moisture to conduct electrical current through any discontinuity in the coating. | P-TI-GR-021 Procedure for Holiday testing | Unless this is pre agreed with the client it could have time, and cost implications during the project.A clear instruction, should be agreed before the contract is finalised. |  | At Tender Review Stage,Planning for storage, Planning for testing, Planning and time and product for repairs., To be checked case by case,Yes ,Holiday testing is time consuming, and will have to be planned into the, schedule,Holiday Test Statement, In certain protective coatings systems, it is important to test the finished coating system for flaws and/or pinholes as these defects can lead to premature, coatings failure in service., This is particularly important if the structure is Primary steel or if it will be used in an immersed or semi-immersed situation. Secondary steel is not, generally holiday tested., It is not reccomended to carry out HV holiday testing over TSZA. Our experience shows DFT's of the metallization generally have a wide variation from, NDFT to several hundred pm., In some spots this may result in a high DFT of metallization and low DFT of coating system. Whilst the total DFT may meet the specification, the low DFT of, coating system in such spots may result in damages to coating and impact accuracy of holiday testing., Testing, The suggested frequency for testing shall be 5% of the total coated surface. The location of the 5% shall be agreed by Tendererlders and the Client Representative prior to testing., A Maximum of 5 findings per 100 m2 of the tested surface are acceptable. A finding is defined as a spot of max. 0,1 m2 with one or various detected pores., In case of more findings and/or one of the spots exceeds the max. size, the next level of testing has to be applied., In case of more then 5 findings per 100 m2 tested surface, additional +10% surface is measured. . If no further pinholes are detected, the coated surface is, accepted. If additional pinholes are detected, the entire coated surface is checked., All findings have to be repaired according the agreed repair procedure., A retest of the repaired spots will not be performed. It is not reccomended by the paint manufacturer and holiday testing the same area more than once, could lead to the unnecessary damages of already Sound coatings., Principle, Porosity in a protective paint system applied to a conductive metal surface is detected either by low-voltage wet-sponge testing or high-voltage spark, testing., Low-voltage pinhole detectors use moisture to conduct electrical current through any discontinuity in the coating.,P-TI-GR-021 Procedure for Holiday testing,Unless this is pre agreed with the client it could have time, and cost implications during the project.A clear instruction, should be agreed before the contract is finalised.
T&I | T&I |  | Pile fixation | The contract price shall be based on a specific type of pile gripper., The Contract shall include a reservation for other suitable means if these are required to accommodate the installation window of the T&I installer. | Gold | Engineering-department, Purchase department | If in ER-Substation | Second gripper system is ca 300 000EUR, 24hr monitoring of pressure of gripper system during early age, grout curing : T&I vessel cost 250 000 EUR - 500 000EUR, All deviations to assumptions made will be handled through VOR | N/A | Following Note to be included in qualification list :, For the design of the grouted connections !between foundation piles and jacket structure) the formulations and verifications as per Norsok N-004 !2021), will be used. This guideline will be used in favour of DNVGL-ST-0126 !and DNVGL-ST-0145) on the basis that the methodology as proposed by the DNV, guidelines has originally been developed for monopile-type foundation and not so much for !pre-piled) jacket type foundations. Even more, DNVGL-, ST_0126 explicitly refers to Norsok N-004 for further recommendations on this type of foundations. Therefore, in order to limit the axial movements within the grouted connection, as per the requirements on Early Age Cycling within Norsok N-004, a single pile gripper ring with horizontal jacks will be included, at the upper regions of the grouted connection assemblies. | N/A | DNVGL-ST-0126 states the relative movement shall be, limited to 1 mm !including both axial and lateral, movement)., Norsok N-004 -2021 states only an axial movement !<0,035%, of pile diameter), The lateral movement, known as Tail Effect, results in extensive movement near the bottom of the grouted, connection, Fe on HKZ, Axial movement is about 1-2 mm,, Lateral near 10 mm | N/A | If in ER-Substation,Second gripper system is ca 300 000EUR, 24hr monitoring of pressure of gripper system during early age, grout curing : T&I vessel cost 250 000 EUR - 500 000EUR, All deviations to assumptions made will be handled through VOR,N/A,N/A,Following Note to be included in qualification list :, For the design of the grouted connections !between foundation piles and jacket structure) the formulations and verifications as per Norsok N-004 !2021), will be used. This guideline will be used in favour of DNVGL-ST-0126 !and DNVGL-ST-0145) on the basis that the methodology as proposed by the DNV, guidelines has originally been developed for monopile-type foundation and not so much for !pre-piled) jacket type foundations. Even more, DNVGL-, ST_0126 explicitly refers to Norsok N-004 for further recommendations on this type of foundations. Therefore, in order to limit the axial movements within the grouted connection, as per the requirements on Early Age Cycling within Norsok N-004, a single pile gripper ring with horizontal jacks will be included, at the upper regions of the grouted connection assemblies.,N/A,DNVGL-ST-0126 states the relative movement shall be, limited to 1 mm !including both axial and lateral, movement)., Norsok N-004 -2021 states only an axial movement !<0,035%, of pile diameter), The lateral movement, known as Tail Effect, results in extensive movement near the bottom of the grouted, connection, Fe on HKZ, Axial movement is about 1-2 mm,, Lateral near 10 mm
NDT | NDT | TES9 | NDT-Procedures | Smulders will work with NDT procedures which have been reviewed and agreed by external, 3rd party it is expected these can be followed without further requirements. All extra, requirements to be excluded from contract price, If fabrication as per DNV-OS-C401:, DNVGL-CG-0051: Non-destructive testing ==> all NDT techniques, If fabrication as per EN1090-2, Different standards per NDT-technique, Purpose is to follow what is given in the standards. | Silver | Technology | If in ER | Required deviations are to be checked by SMU level 3, to be, checked on feasability and extra cost. | Required deviations are to be checked, by SMU level 3, to be checked on, feasability and extra cost. | Smulders has for each Technique a standard procedure reviewed by DNV available., These are followed without extra requirements. | Standard NDT procedures | see impact cost/planning | N/A | If in ER,Required deviations are to be checked by SMU level 3, to be, checked on feasability and extra cost.,N/A,Required deviations are to be checked, by SMU level 3, to be checked on, feasability and extra cost.,Smulders has for each Technique a standard procedure reviewed by DNV available., These are followed without extra requirements.,Standard NDT procedures,see impact cost/planning
NDT | NDT | TES8 | NDT-Calibration Blocks | Project specific calibration blocks to be used for the project, DNVGL-CG-0051:, a general-purpose block of uniform low attenuation and specified surface finish, and, having a thickness within ± 10% of the test object a block of the same acoustic properties, surface finish, shape and curvature as the test, object., ISO 16811: a general-purpose block of uniform low attenuation and specified surface finish, and, having a thickness within ± 10% of the test object, a block of the same acoustic properties, surface finish, shape and curvature as the test, object. | Silver | Technology | If in ER | extra calibration blocks to be made:, Cost of blocks:, Normal steel: 250 Euro / block !for each type of block required one block needs to be fabricated, one block is required for each, fabrication facility), TMCP steel: 250 Euro/block !for TMCP steel for each type of block, needed a block in rolling direction and transverse on rolling direction is required and a set of both blocks is required for each, fabrication site). | N/A | Several reference blocks available per site., Available blocks cover majority of scope, Specific reference block needed !Design) ==> available as required per NDT standard., Blocks with similar material as used in project, Blocks from specific project material is excluded from the contract., For thickness range of blocks SMU follows DNVGL !the 10% as per EN standard will not be followed). | N/A | see impact cost | N/A | If in ER,extra calibration blocks to be made:, Cost of blocks:, Normal steel: 250 Euro / block !for each type of block required one block needs to be fabricated, one block is required for each, fabrication facility), TMCP steel: 250 Euro/block !for TMCP steel for each type of block, needed a block in rolling direction and transverse on rolling direction is required and a set of both blocks is required for each, fabrication site).,N/A,N/A,Several reference blocks available per site., Available blocks cover majority of scope, Specific reference block needed !Design) ==> available as required per NDT standard., Blocks with similar material as used in project, Blocks from specific project material is excluded from the contract., For thickness range of blocks SMU follows DNVGL !the 10% as per EN standard will not be followed).,N/A,see impact cost
NDT | NDT | TES7 | NDT Hold times | Hold times exceeding times as per standards should not be accepted, for DNVGL projects it, should be agreed that the reduced hold time to 24hours as per standard is agreed., For Repairs no hold time to be allowed for steels with SMYS <360MPa, When Fabrication is to be perfomred as per EN 1090-2 ==> hold times of table 23 of the EN 1090-2 to be, applicable without exception., The hold time for NDT is implemented to detect possible delayed cracking within welds. Delayed cracking !HIC/cold cracking) occurs in welds due to a combination of 3 factors !Hydrogen, high hardness and high, internal stresses) coming together in the weld. Smulders takes the necessary action to limit the occurence of, these factors as much as possible and No issues with delayed cracking have occured in the latest projects executed by Smulders., This delayed cracking of welds has no relation to the standard weld defects related to the process, welder,... and therefore there is no relation with a standard defect rate and applicable hold time for NDT., Statement document R-TI-GR-301 can be used to provide to employer to agree on reduced hold time. | Silver | Technology | If in ER, Topside Serial Project, No impact for Jacket | Cost impact : if 48hr remain in stead of 24hr, For each TP : 4000€ for mainstructure & 2000€ for secondary steel, Rental cost for rollers & additional personnel !to perform, prechecks and avoid standstill), Storage area, more handling !additional personnel) & rental cost, cranes, Topside : 1hr per Ton Civil : 1hr per Ton, No extra cost for Jacket | Increase in lead time for production, !possible blockage at bottlenecks), Example: small superficial repair work, after blasting in blasting shop | according to standards:, As per standard with remark, DNV-project : Ask for reduction to 24 hrs., 1st option: Provide statement R-TI-GR-301 with previous experience 2nd option: Proposal 48 hrs. first X-pieces then reduced !still impact!, but limited), EN: as per table Method A = SMYS < 420 Mpa, Method B = SMYS > 420 Mpa, Repair, Superficial: no hold time (Dept of repair < 5mm) Volumetric: as per original weld | R-TI-GR-301 Statement subject to agreement !NDT hold time) | see impact cost/planning | N/A | If in ER, Topside Serial Project, No impact for Jacket,Cost impact : if 48hr remain in stead of 24hr, For each TP : 4000€ for mainstructure & 2000€ for secondary steel, Rental cost for rollers & additional personnel !to perform, prechecks and avoid standstill), Storage area, more handling !additional personnel) & rental cost, cranes, Topside : 1hr per Ton Civil : 1hr per Ton, No extra cost for Jacket,N/A,Increase in lead time for production, !possible blockage at bottlenecks), Example: small superficial repair work, after blasting in blasting shop,according to standards:, As per standard with remark, DNV-project : Ask for reduction to 24 hrs., 1st option: Provide statement R-TI-GR-301 with previous experience 2nd option: Proposal 48 hrs. first X-pieces then reduced !still impact!, but limited), EN: as per table Method A = SMYS < 420 Mpa, Method B = SMYS > 420 Mpa, Repair, Superficial: no hold time (Dept of repair < 5mm) Volumetric: as per original weld,R-TI-GR-301 Statement subject to agreement !NDT hold time),see impact cost/planning
NDT | NDT | TES6 | NDT RT/UT replacement | Radiographic testing can't be replaced by manual or recorded UT is not to be accepted, !note: exception is made for bridges, where this is a requirement of the standard, if not, acceptable by employer cost to be taken into account)., DNV-OS-C401:, 2) RT is required. RT may be partly or wholly replaced by UT upon agreement. For hull, welds the minimum length inspected by RT is typically 300 mm. Consideration may be given for reduction of inspection frequency for automated welds where quality assurance, techniques indicate consistent satisfactory quality | Silver | Technology | If in ER | Cost of RT to be taken into account, For Darmstadt RT was required on 1 of the 4 bridge and had a cost, of 50000 euro, For Rx other than bridges : contact TE | If RT is to be performed, either part of, fabricaiton hall is to be closed for RT, inspection or piece have to be sent to, a covered location. Extra lead time for, parts which are prone to RT inspections | Request to be made to replace RT inspection by manual UT or recorded UT if manual UT is not accepted. | R-TI-GR-31, inspection 2 statement - replacing RT by UT | This request has different sides:, -From a technical point of view: For certain connections !T-, connections, thicker material thicknesses,...) it is practically, not feasible to make qualitative radiographs from the, welded connections due to the limitations of the, inspections technique., -From a HSE perspective: RT uses x- or gamma-rays to, perform volumetric inspection of welds which can be, harmfull for people, for this reason RT can only be, performed after a certain is set-off or when no-one is, working in the area., -from a planning prespective: Due to fact that the RT, inspections can only be performed when nobody is in the, proximity of the to be tested weld, it can only be performed, at planned moments while UT inspection can be performed, while other works are ongoing in the proximity., See statement R-TI-GR-312 statement - replacing RT by UT, inspection | N/A | If in ER,Cost of RT to be taken into account, For Darmstadt RT was required on 1 of the 4 bridge and had a cost, of 50000 euro, For Rx other than bridges : contact TE,N/A,If RT is to be performed, either part of, fabricaiton hall is to be closed for RT, inspection or piece have to be sent to, a covered location. Extra lead time for, parts which are prone to RT inspections,Request to be made to replace RT inspection by manual UT or recorded UT if manual UT is not accepted.,R-TI-GR-31, inspection 2 statement - replacing RT by UT,This request has different sides:, -From a technical point of view: For certain connections !T-, connections, thicker material thicknesses,...) it is practically, not feasible to make qualitative radiographs from the, welded connections due to the limitations of the, inspections technique., -From a HSE perspective: RT uses x- or gamma-rays to, perform volumetric inspection of welds which can be, harmfull for people, for this reason RT can only be, performed after a certain is set-off or when no-one is, working in the area., -from a planning prespective: Due to fact that the RT, inspections can only be performed when nobody is in the, proximity of the to be tested weld, it can only be performed, at planned moments while UT inspection can be performed, while other works are ongoing in the proximity., See statement R-TI-GR-312 statement - replacing RT by UT, inspection
NDT | NDT | TES5 | NDT Repair reports | Full reporting of VT, MT or PT repairs to be reported is to be avoided. | Silver | Technology | If in ER | Extra NDT cost, extra manpower QC follow-up | N/A | VT-MT-PT !superficial NDT), Indications marked on the piece for rework, Re-testing after rework, Report made after rework to approve piece, Except: if crack-indication is found this will be seperatly reported, UT, If non-acceptable indication is found ==> report will be made, Re-test after repair ==> new report will be made, Acceptable indications will be reported as per standard, Signature on report by either:, Operator who performed inspection, Level 3 of NDT company who performed inspection | P-TI-GR-063 | If all VT, MT or PT repairs have to be documented this, means extra time !cost) is to be taken into account for NDE, testing, QC folllow-up and document control. This has no, added value as majority of the indications found by these, test can be solved by grinding works or minor welding, !superficial). It has no added value to have this traceable as, this are works which could have been performed by a, welder as well during his works., It can be highlighted that if crack-like indications are found, they will be reported., Within the document P-TI-GR-063 it is described how, different defects superficial or volumetric are treated and, reported. The purpose should be that it is agreed with, employer that this way forward can be followed. | N/A | If in ER,Extra NDT cost, extra manpower QC follow-up,N/A,N/A,VT-MT-PT !superficial NDT), Indications marked on the piece for rework, Re-testing after rework, Report made after rework to approve piece, Except: if crack-indication is found this will be seperatly reported, UT, If non-acceptable indication is found ==> report will be made, Re-test after repair ==> new report will be made, Acceptable indications will be reported as per standard, Signature on report by either:, Operator who performed inspection, Level 3 of NDT company who performed inspection,P-TI-GR-063,If all VT, MT or PT repairs have to be documented this, means extra time !cost) is to be taken into account for NDE, testing, QC folllow-up and document control. This has no, added value as majority of the indications found by these, test can be solved by grinding works or minor welding, !superficial). It has no added value to have this traceable as, this are works which could have been performed by a, welder as well during his works., It can be highlighted that if crack-like indications are found, they will be reported., Within the document P-TI-GR-063 it is described how, different defects superficial or volumetric are treated and, reported. The purpose should be that it is agreed with, employer that this way forward can be followed.
Final assembly | Final assembly | TES4 | Mechanical Grating gaps | Ball size of gratings + gap with wall should be in line with the applicable standards,, deviations from the standard should be checked if practically feasible., Safety of machinery - permanent means of access to machinery, ISO 14122-2: Working platforms and walkways | Silver | Technology/Engineering/PD | If in ER | To be checked project specific | To be checked project specific | As per standard | Roadbook TPs: under construction, Roadbook t,opsides:, https://intranet.smulders.com/sites/IMS/_layout, s/15/WopiFrame.aspx?sourcedoc=%7B6DBA4248-, BD18-44D9-B5BB-42793C39F99D%7D&file=P-TI-, GR-090%20Inspection%20Roadbook%20-, %20HAT%27s.docx&action=default&DefaultItemO, pen=1 | To be checked with Commercial department what is feasible, from grating supplier, Cover plates to be used, Extra parts to be installed next to gratings, Extra material needed, Extra work hours needed, There is a limit on practical tolerances. | N/A | If in ER,To be checked project specific,N/A,To be checked project specific,As per standard,Roadbook TPs: under construction, Roadbook t,opsides:, https://intranet.smulders.com/sites/IMS/_layout, s/15/WopiFrame.aspx?sourcedoc=%7B6DBA4248-, BD18-44D9-B5BB-42793C39F99D%7D&file=P-TI-, GR-090%20Inspection%20Roadbook%20-, %20HAT%27s.docx&action=default&DefaultItemO, pen=1,To be checked with Commercial department what is feasible, from grating supplier, Cover plates to be used, Extra parts to be installed next to gratings, Extra material needed, Extra work hours needed, There is a limit on practical tolerances.
Fab & QC | Fab & QC | TES3 | Additional Qualification of personnel | Qualified personnel to be in line with fabrication standards, no seperate qualifications should be accepted without agreement. | Silver | Technology QA/QC managers sites | If in ER | If employer request extra qualifcations on top of requirements of, standard:, Cost to cover these requirement to be excluded from contract | N/A | As per the standards, As per the organigram and job descriptions taken into account into the difference quality management certificates., Standards describe which level of qualification is required for certain inspections., Some examples:, Welders : EN ISO 9606-1 Weld operators: EN ISO 14732, Welding coordination: As per the NDT standard | Reference to, -lists of qualified personnel !welders/NDT, operators, painters,....), -organization charts -Company quality certificates | To be checked what is feasible, Availability qualified persons, Extra certifications !trainings available, planning of trainings,...), ... | N/A | If in ER,If employer request extra qualifcations on top of requirements of, standard:, Cost to cover these requirement to be excluded from contract,N/A,N/A,As per the standards, As per the organigram and job descriptions taken into account into the difference quality management certificates., Standards describe which level of qualification is required for certain inspections., Some examples:, Welders : EN ISO 9606-1 Weld operators: EN ISO 14732, Welding coordination: As per the NDT standard,Reference to, -lists of qualified personnel !welders/NDT, operators, painters,....), -organization charts -Company quality certificates,To be checked what is feasible, Availability qualified persons, Extra certifications !trainings available, planning of trainings,...), ...
Fab & QC | Fab & QC | TES2 | Welding supervision | No maximum amount of people supervised by one supervisor should be allowed. Smulders should be able to organize it's production supervision without limits. | Silver | Production managers sites | If in ER | If ER describe specific amount of supervisor, qualifications of, supervisors, work hours,..., To be checked with production sites if this is standard., If yes: No problem, If No: to be checked:, -Extra cost for extra personnel?, -Are these extra persons available on the market? | N/A | Smulders has certification according the different quality standards, workshop are organized to comply to the quality standards, Certification of companies is done according to quality standards:, EN1090-2, EN3834-series, DNV Workshop approvals, Deutsche Bahn, ... Certification to these quality standards prove a system to guarantee the quality in production is in place. | Reference to SMU quality management, certificates | The smulders organization is certified according quality, standards: EN 1090-2 !3834-2), and DNVGL workshop, approvals. These certification also cover the fact how quality, is assured on the work floor, it therefore up to Smulders to, organize the workshop en supervision of the workers. | N/A | If in ER,If ER describe specific amount of supervisor, qualifications of, supervisors, work hours,..., To be checked with production sites if this is standard., If yes: No problem, If No: to be checked:, -Extra cost for extra personnel?, -Are these extra persons available on the market?,N/A,N/A,Smulders has certification according the different quality standards, workshop are organized to comply to the quality standards, Certification of companies is done according to quality standards:, EN1090-2, EN3834-series, DNV Workshop approvals, Deutsche Bahn, ... Certification to these quality standards prove a system to guarantee the quality in production is in place.,Reference to SMU quality management, certificates,The smulders organization is certified according quality, standards: EN 1090-2 !3834-2), and DNVGL workshop, approvals. These certification also cover the fact how quality, is assured on the work floor, it therefore up to Smulders to, organize the workshop en supervision of the workers.
Fab & QC | Fab & QC | TES14 | Seafastening | Seafastening that has to comply to project requirements and not standard rules ==> Seafastening should be fabrcated as per DNV or EN standard | Silver | Technology/Prod | If in ER | cost for exta NDT, more time inspection, different materials, more, preheat, routercards ==> to be calculated extra per ton steel | Yes as mostly new seafastening is to be, build and no or limited re-use possible,, extra fabrication time | Reuse of existing, standard reporting, extend of testing visual less strict and minimum preheat, |  | extra cost if client request this and reuse maybe not possible, so should be new built |  | If in ER,cost for exta NDT, more time inspection, different materials, more, preheat, routercards ==> to be calculated extra per ton steel,Yes as mostly new seafastening is to be, build and no or limited re-use possible,, extra fabrication time,Reuse of existing, standard reporting, extend of testing visual less strict and minimum preheat,,extra cost if client request this and reuse maybe not possible, so should be new built
Welding | Welding | TES13 | Preheating | Why preheat:, Limit the chances on cold cracking of the welds, Linked to through thickness quality of the material Avoid High hardness in weld area (mainly HAZ) - WPQRs, Based on CTOD qualification of base material The EN standard EN-1011-2 describes 2 methods !A and B), Both methods depend on different parameters of the connection. Method A, mainly used for the normal and high strength steels !up to SMYS of 420MPa) Method B, Extra high strength steel | Silver | Technology-department | If in ER | Method B, Topside : to be checked case by case thickness over 25 mm ! Columns, node, change Jacket: 1,5 hr/Ton, Method A : 1hr per Ton, For serial projects to be determined on case by case. Expected, impact on wall thickness over 25 mm ! e.g boatlanding), below 25 mm no change, Expected impact on wall s etc.) below 25 mm no | More preheating will have to be performed resulted in longer lead, times of the welding works. | -Normal and high strength Steel with SMYS <S355, similar to Method A of the EN 1011-2 taking into account WPQRS, Based on combined thickness, -extra high strength steel (SMYS >420MPa) based on thickness of the thickest member in the connection, similar to method B of the EN 1011-2 taking into account WPQRS, Standard preheat is performed with gas burners. Only for items which require higher preheat temperatures !>100°C), higher thicknesses, etc... It is possible, to implement electrical heating 0 As per standard | Standard S MU weld plan | Method B to determine preheat, -smaller thickness plates need to be preheated 0 possibly, bigger deformations, - is based on the thickness of the thickness member in the, connection 0 more connections 0 extra time required to perform, - Calculations for preheat to be p connections 0 extra QC hrs, - Use of electrical preheating will increase cost/lead time of production !available preheating machines, cost for rental,, installation of preheat equipment,etc...). will need to be preheated welding works., erformed for certain | N/A | If in ER, Method B, Topside : to be checked case by case thickness over 25 mm ! Columns, node, change Jacket: 1,5 hr/Ton, Method A : 1hr per Ton, For serial projects to be determined on case by case. Expected, impact on wall thickness over 25 mm ! e.g boatlanding), below 25 mm no change, Expected impact on wall s etc.) below 25 mm no,N/A,More preheating will have to be performed resulted in longer lead, times of the welding works.,-Normal and high strength Steel with SMYS <S355, similar to Method A of the EN 1011-2 taking into account WPQRS, Based on combined thickness, -extra high strength steel (SMYS >420MPa) based on thickness of the thickest member in the connection, similar to method B of the EN 1011-2 taking into account WPQRS, Standard preheat is performed with gas burners. Only for items which require higher preheat temperatures !>100°C), higher thicknesses, etc... It is possible, to implement electrical heating 0 As per standard,Standard S MU weld plan,Method B to determine preheat, -smaller thickness plates need to be preheated 0 possibly, bigger deformations, - is based on the thickness of the thickness member in the, connection 0 more connections 0 extra time required to perform, - Calculations for preheat to be p connections 0 extra QC hrs, - Use of electrical preheating will increase cost/lead time of production !available preheating machines, cost for rental,, installation of preheat equipment,etc...). will need to be preheated welding works., erformed for certain
Welding | Welding | TES12 | Weld Procedure Qualification Record (WPQR) | Welding is a special process ==> Destructive testing only way to be 100% sure, Fabrication standards e.g. EN, DNV, AWS,... ==> qualification of weld process based on:, -Ranges on material !thickness, Heat-input, diameters, material grade, etc...), -Which tests to be performed, -How to document .-,.., These are based theoretical models and on experience gained over the years from the experts in norms and standard commissions., To give as much as possible assurance on the quality of the welds !together with NDT)., Amount of WPQRs to cover a WPS will not be limited. | Silver | Technology-department | If in ER | If extra WPQRs need to be welded cost has to be taken into, account:, Butt weld test piece (*50mm): 5600 EUR, Fillet weld test piece (*30mm): 2300 EUR, For S355-S420 material !substation/jacket/TP), 10 WPQR's needed EN 1090: €42 800, 20 WPQR's needed DNV-OS-C401: €85 600, For S460 and up : ask advise TE | N/A | Database of WPQRs based on EN 15614 and/or DNV-OS-C401:, -Test performed as per edition of standard at time test is performed -Most WPQR qualified according both EN15614 and DNV-OS-C401, -WPS are made by combining several WPQRs to cover ranges -All WPQRs witnessed by 3rd party (DNV or Lloyd's), -Packages with WPSs accordign to standards signed by DNV available | Standard weld plans available for EN1090 or DNV-, OS-C401 projects | See impact on cost, C-content and CE limlitiations to be listed | N/A | If in ER,If extra WPQRs need to be welded cost has to be taken into, account:, Butt weld test piece (*50mm): 5600 EUR, Fillet weld test piece (*30mm): 2300 EUR, For S355-S420 material !substation/jacket/TP), 10 WPQR's needed EN 1090: €42 800, 20 WPQR's needed DNV-OS-C401: €85 600, For S460 and up : ask advise TE,N/A,N/A,Database of WPQRs based on EN 15614 and/or DNV-OS-C401:, -Test performed as per edition of standard at time test is performed -Most WPQR qualified according both EN15614 and DNV-OS-C401, -WPS are made by combining several WPQRs to cover ranges -All WPQRs witnessed by 3rd party (DNV or Lloyd's), -Packages with WPSs accordign to standards signed by DNV available,Standard weld plans available for EN1090 or DNV-, OS-C401 projects,See impact on cost, C-content and CE limlitiations to be listed
Project set-up | Project set-up | TES11 | Traceability | traceability more stringent than:, Special steel:, Material related: Unique traceability, Welding related: traceability with RC containing following info: welder, WPS, welding, consumable, NDT data, Primary steel:, Material related: full !not unique) traceability Welding related: traceability with RC containing following info: Welder, WPS, NDT data, Secondary steel:, Material related: grouped traceability, Welding related: mentioning of Welders on DWG, Report with highlighted drawing for NDT., Traceability of welds of secondary steel against primary steel to be treated as secondary, steel !exception is made for welds of secondary steel items against the primary steel cans, of a TP foundation)., Tertiary steel:, Material related: traceable back to supplierd, Welding related: no traceability only if NDT is performed. | Silver | Technology/Engineering | If in ER | Extra works Engineering drawing office:, Extra works QA/QC to keep traceability:, Extra cost subcontractors -for engineering 0,25 hr per Ton, -0,5 FTE extra/facility during welding period, The above values to be taken X2 if unique traceability is applicable, for secondary steel, For serial projects 15 KEuro fix +2,5-3k Euro/TP-MP | N/A | Serial TP & Jacket: compliant to Standard One off, ->Topside: Primary no RC, only special RC, ->Jacket: Primary& Special RC, Remark: No Unique traceability will be applied | P-TI-GR-101 Traceability procedure one-off, projects.docx, P-TI-GR-102 Traceability procedure serial, projects.docx | All deviation from standard traceability require extra work,, more position numbers to be created, Subcontractors to, provide extra information, extra follow-up etc..., Cost calculation to be made project specific ==> to be, checked on project basis | N/A | If in ER,Extra works Engineering drawing office:, Extra works QA/QC to keep traceability:, Extra cost subcontractors -for engineering 0,25 hr per Ton, -0,5 FTE extra/facility during welding period, The above values to be taken X2 if unique traceability is applicable, for secondary steel, For serial projects 15 KEuro fix +2,5-3k Euro/TP-MP,N/A,N/A,Serial TP & Jacket: compliant to Standard One off, ->Topside: Primary no RC, only special RC, ->Jacket: Primary& Special RC, Remark: No Unique traceability will be applied,P-TI-GR-101 Traceability procedure one-off, projects.docx, P-TI-GR-102 Traceability procedure serial, projects.docx,All deviation from standard traceability require extra work,, more position numbers to be created, Subcontractors to, provide extra information, extra follow-up etc..., Cost calculation to be made project specific ==> to be, checked on project basis
NDT | NDT | TES10 | NDT-Extent | Extent of NDT beyond as specified within standards ==> extra cost to be calculated., The extra extent is to be given on project specific level by TE reviewer., - Extra NDT on secondary or primary steel then specified in fabrication standards. - UT inspection on FW/PP welds, -... | Silver | Technology | If in ER | Depending on scope of extra NDT, - Cost calculation? ==> price/ton to be increased. Serial projects, calculated case by case by production sites. ! Cost Calculator, informs production sites) | Depending on scope of extra NDT | NDT extent as defined in, DNV-OS-C401, EN1090-2 | Standard ITPs | see impact cost/planning | N/A | If in ER,Depending on scope of extra NDT, - Cost calculation? ==> price/ton to be increased. Serial projects, calculated case by case by production sites. ! Cost Calculator, informs production sites),N/A,Depending on scope of extra NDT,NDT extent as defined in, DNV-OS-C401, EN1090-2,Standard ITPs,see impact cost/planning
Fab & QC | Fab & QC | TES1 | Backing strips | Permanent backing strips should at least be accepted for non fatigue critical welds !e.g., Secondary steel)., EN 1090-2:, Allows the use of permanent backing strips with following restrictions on the backings strip:, CEV, Location of tack welding, Backing strip to be continuous, DNV-OS-C401:, The use of permanent steel backing strips may be accepted after thorough corrosion evaluation and when accounted for in the design analysis with resepect to fatigue:, ==> Focus is mainly on fatigue: fatigue classes, Butt weld one side without backing 0 class W3, Butt weld one side with backing 0 class F | Silver | Technology?Engineering | If in ER | To be calculated case by case | Possible extra lead time for repairs | Smulders Way, Permanent steel backing strips should be allowed on: On static welded connections, Welded connections which, with backing strip can be designed with improved fatigue detail., Increased fit-up tolerances, Easier for the welder less risk on mistakes in the root, Note: check on corrosion sensitivity is to be performed. | P-TI-GR-068: wide gap and backing strips, instruction | reference is made to Statement: P-TI-GR-068: wide gap and, backing strips instruction | N/A | If in ER,To be calculated case by case,N/A,Possible extra lead time for repairs,Smulders Way, Permanent steel backing strips should be allowed on: On static welded connections, Welded connections which, with backing strip can be designed with improved fatigue detail., Increased fit-up tolerances, Easier for the welder less risk on mistakes in the root, Note: check on corrosion sensitivity is to be performed.,P-TI-GR-068: wide gap and backing strips, instruction,reference is made to Statement: P-TI-GR-068: wide gap and, backing strips instruction
Project set-up | Project set-up | TES15 | Method Statements/procedures | The Contract/MDR] shall include a defined timescale for when these, Procedures/Methode Statements/Contractor's documents] will be in place and this must, be prior to any fabrication/manufacturing/installation activities commencing., Said timescale will include adequate time for the Employer to review such procedures, but, will be linked to a strict deadline as not to hamper Contractor's production schedule., Specific timescales will be included in the contract for, but not limited to, reviews by a certification body and a marine warranty surveyor. ! more than 28 days to be flagged), The principle of exhaustive commenting shall apply during the approval process of the documents, If the Employer fails to review the documents within the stated timescale over 4 weeks ,, the document will be deemed to be accepted without any comments., Contractor may proceed with the fabrication/manufacturing/installation activities relating, to parts of the documents that is not rejected. | Silver | Doc controller /Technology/Engineering | Always | -Extra hours to perform the extra review cycles, -Extra hours to perform the extra review cycles, - Extra effort to fix issues that are not adressed in previous version, of the document -Not possible to quantify impact since multiple disciplines! e.g, -Not possible to quantify impact since multiple disciplines! e.g, Technology, engineering) invovled. | -Delay of Start of production -Delay of Production planning | The contractor's proposal is based on the understanding that comments on a second revision should not address topics that were already present but left, unaddressed in the first revision. Introducing new feedback at this stage on previously available content is not considered viable., Any changes to this proposal may have cost and planning implications for the project. Such impacts will be communicated through the Variation Order, !VOR) process. Employer representatives attending inspections must have the authority to sign and validate inspection records and related documents. This should be, clarified in advance by the EMP project team prior to the start of inspections., By default, any individual delegated by EMP to attend an inspection will be deemed to hold this authority, and their signature will be considered valid. |  | Dealing with multiple review cycle the comments that were not adressed before | N/A | Always,-Extra hours to perform the extra review cycles, -Extra hours to perform the extra review cycles, - Extra effort to fix issues that are not adressed in previous version, of the document -Not possible to quantify impact since multiple disciplines! e.g, -Not possible to quantify impact since multiple disciplines! e.g, Technology, engineering) invovled.,N/A,-Delay of Start of production -Delay of Production planning,The contractor's proposal is based on the understanding that comments on a second revision should not address topics that were already present but left, unaddressed in the first revision. Introducing new feedback at this stage on previously available content is not considered viable., Any changes to this proposal may have cost and planning implications for the project. Such impacts will be communicated through the Variation Order, !VOR) process. Employer representatives attending inspections must have the authority to sign and validate inspection records and related documents. This should be, clarified in advance by the EMP project team prior to the start of inspections., By default, any individual delegated by EMP to attend an inspection will be deemed to hold this authority, and their signature will be considered valid.,Dealing with multiple review cycle the comments that were not adressed before
NDT | NDT | TEB9 | VT inspection | Waiting time in standard includes VT inspection but on our scope of work the VT inspection, will not be different after welding and after 48 or 24 hours | Bronze | Technology/Prod | If in ER | Needs to be discussed with production. Not for all welds, applicable but mainly on secondary steel !percentage) this can, result in a loose of production time. 1 or 2 days extra between, welding and blasting per item possible. | yes |  |  | extra time needed |  | If in ER,Needs to be discussed with production. Not for all welds, applicable but mainly on secondary steel !percentage) this can, result in a loose of production time. 1 or 2 days extra between, welding and blasting per item possible.,yes,extra time needed
Prod | Prod | TEB8 | TKY joints secondary steel | IF an EN project TKY joint is not clear how the weld volume shoud be. AWS D1.1 to be, included | Bronze | Technology/Prod | IF EN TP project | Extra cost for welding volume when robot used !SPP has, information) | no | AWS D1.1 to be used on robot welding | P-TI-TI-GR46 | extra welding cost due to loss productivity |  | IF EN TP project,Extra cost for welding volume when robot used !SPP has, information),no,AWS D1.1 to be used on robot welding,P-TI-TI-GR46,extra welding cost due to loss productivity
O&M | O&M | TEB7 | O&M | If design is done by client, designer is responsible for O&M for structural items. | Bronze | Engineering/PM | If design is not done internal | TBD | no | designer determines in his design already requiremend so should be wavered by ours |  |  |  | If design is not done internal,TBD,no,designer determines in his design already requiremend so should be wavered by ours
Project set-up | Project set-up | TEB6 | Design involvement (for inspration) | Design constraints ==> Follow-up by Smulders, -Thickness class C for secondary steel or lower or for primary steel in small batch !e.g., Batches too small to order from mill) can't be accepted as this is almost not available on, the market., -Z-quality of steel to be specified by the designer and should only be applied where, specifically required for design technical reason. It should not be the purpose that Z-steel is required everywhere., -Fatigue classification welds and holes should take into account possible repairs, a method, should be agreed up front !e.g. Weld repair or increasing the cut-out size). | Bronze | Engineering/Technology | If in ER | Project specific | project specific | Works are to be performed according fabrication standard based on the chosen design standard !and/or local applicable laws, f.e. BSH-requirements)., For Items missing in a fabrication standard reference can be made to another fabrication standard., Purpose is not to combine different standards and choose the most stringent, as design standards don't take this into account., Extra requirements of employer on certain items will not change design life of a structure or improve the quality !see some examples):, Increased thickness tolerance base material, Narrowed qualification ranges of WPQRs, Purpose should also be to be involved in design as soon as possible:, Avoid non-executable connections, Avoid unnecessary/ impractical stringent fatigue clases, Avoid unnecessary stringent tolerances | N/A | Certain requirements can impact different stages:, Material availability !thickness tolerance class, Z-quality,, surface condition,...), Feasibility, Fabrication lead time, .... | N/A | If in ER,Project specific,N/A,project specific,Works are to be performed according fabrication standard based on the chosen design standard !and/or local applicable laws, f.e. BSH-requirements)., For Items missing in a fabrication standard reference can be made to another fabrication standard., Purpose is not to combine different standards and choose the most stringent, as design standards don't take this into account., Extra requirements of employer on certain items will not change design life of a structure or improve the quality !see some examples):, Increased thickness tolerance base material, Narrowed qualification ranges of WPQRs, Purpose should also be to be involved in design as soon as possible:, Avoid non-executable connections, Avoid unnecessary/ impractical stringent fatigue clases, Avoid unnecessary stringent tolerances,N/A,Certain requirements can impact different stages:, Material availability !thickness tolerance class, Z-quality,, surface condition,...), Feasibility, Fabrication lead time, ....
Final assembly | Final assembly | TEB4 | Project completion tool | Use of a Project completion tool, used to keep track of status of each tagged item in a, project, including technical information for the tags. !e.g. ProCoSys) | Bronze | Doc controller | If in ER | The use of !ProCoSys) gives a significant extra workload to DCC, and ABC !1.5 FTE additional needs to be taken into account), Note: always take into account the complexity and size of the, project | Training of staff necessary | ERP/PITS | N/A | N/A | N/A | If in ER,The use of !ProCoSys) gives a significant extra workload to DCC, and ABC !1.5 FTE additional needs to be taken into account), Note: always take into account the complexity and size of the, project,N/A,Training of staff necessary,ERP/PITS,N/A,N/A
Fab & QC | Fab & QC | TEB3 | Traceability | Requirement to have traceability of preheat values for certain steel categories; | Bronze | Technology | If in ER |  | N/A | Preheat is not recorded as this is not specified in the different fabrication standards | N/A | see impact cost | N/A | If in ER,N/A,N/A,Preheat is not recorded as this is not specified in the different fabrication standards,N/A,see impact cost
Fab & QC | Fab & QC | TEB2 | Inspections: documentation | Document related to inspections !e.g. NDE-reports, Dimensional reports) should only be, available at certain inspection steps !e.g. Black steel inspection). We can't guarantee that, reports like NDE or Dimensional reports can/will be provided to Employer x hours after, inspection. | Bronze | Technology/PRO | If in ER | Extra manpower to be made available for:, NDT personnel, QC personnel | If client request documentation before, inspection to be final, possible delay in, planning due to:, Postponement of inspections due to, not available papers | Document related to inspections !e.g. NDE-reports, Dimensional reports) will be available at certain inspection steps !e.g. Black steel inspection). These are, possibly only draft versions !work version from workshop)., We can't guarantee that final reports such as NDE or Dimensional reports can/will be provided to Employer x hours after inspection. Weld related reporting shall be however available after coating works | N/A | N/A | N/A | If in ER,Extra manpower to be made available for:, NDT personnel, QC personnel,N/A,If client request documentation before, inspection to be final, possible delay in, planning due to:, Postponement of inspections due to, not available papers,Document related to inspections !e.g. NDE-reports, Dimensional reports) will be available at certain inspection steps !e.g. Black steel inspection). These are, possibly only draft versions !work version from workshop)., We can't guarantee that final reports such as NDE or Dimensional reports can/will be provided to Employer x hours after inspection. Weld related reporting shall be however available after coating works,N/A,N/A
Technology | Technology | TEB1 | Temporary attachments | Use of temporary attachments with regards to allowed locations and traceability., The use of temporary attachments should be standardly allowed with exclusion of certain, areas. The purpose should be that on the design drawings designer clearly marks the, locations where temporary attachements are not acceptable., Full traceability of temporary attachements to be avoided, this can be accepted for special steel but for primary or lower category, only NDT report after removal to be provided, without traceability of locations | Bronze | Technology | If in ER | If no temporary attachemnts are allowed this could increase cost, as other ways for assembly of the project are to be considered., If full traceability is required Extra follow-up cost, Impact is depending on project and level of restriction /, traceability, But can be priced | If no temporary attachemnts are, allowed this could increase lead time, as other ways for assembly of the, project are to be considered. | Temporary attachments are required to assemble certain items before welding to already give some temporary structural strenght., To be allowed everywhere !except where highlighted on design drawings), No traceability of used material (All grades with SMYS < 460MPa should be allowed), Not to be included on WSD and/or ASB drawings, With regards to removal, Cut 3mm above base material, Grind flush VT+MT to be performed, 1 Report to cover all locations of temporary attachments !no traceability to locations). | Temporary attachment procedure: P-TI-GR-094 | During Fabrication of steel structures the use of temporary, attachments !f.e. Welding bridges, temporary lifting points,, etc.) is sometimes required to allow qualitative assembly of, the structure before start of welding works and/or for safe, handling of components., Smulders will weld these temporary attachments to the, structure using the WPSs included in the project specific, weld plan, removal of the attachments will be performed as, per good industry practice !cutting 3mm above surface,, grinding and performing VT and MT) to assure there is no, negative effect on the base material of the steel structure. It can be agreed that for certain locations !f.e. areas around, fatigue critical welds) it will be marked on drawings that, temporary attachements are not allowed. But for the other, locations it should be agreed that free use of temporary, attachments is allowed and no traceability of these locations, is to be kept as this has no technical value. | N/A | If in ER,If no temporary attachemnts are allowed this could increase cost, as other ways for assembly of the project are to be considered., If full traceability is required Extra follow-up cost, Impact is depending on project and level of restriction /, traceability, But can be priced,N/A,If no temporary attachemnts are, allowed this could increase lead time, as other ways for assembly of the, project are to be considered.,Temporary attachments are required to assemble certain items before welding to already give some temporary structural strenght., To be allowed everywhere !except where highlighted on design drawings), No traceability of used material (All grades with SMYS < 460MPa should be allowed), Not to be included on WSD and/or ASB drawings, With regards to removal, Cut 3mm above base material, Grind flush VT+MT to be performed, 1 Report to cover all locations of temporary attachments !no traceability to locations).,Temporary attachment procedure: P-TI-GR-094,During Fabrication of steel structures the use of temporary, attachments !f.e. Welding bridges, temporary lifting points,, etc.) is sometimes required to allow qualitative assembly of, the structure before start of welding works and/or for safe, handling of components., Smulders will weld these temporary attachments to the, structure using the WPSs included in the project specific, weld plan, removal of the attachments will be performed as, per good industry practice !cutting 3mm above surface,, grinding and performing VT and MT) to assure there is no, negative effect on the base material of the steel structure. It can be agreed that for certain locations !f.e. areas around, fatigue critical welds) it will be marked on drawings that, temporary attachements are not allowed. But for the other, locations it should be agreed that free use of temporary, attachments is allowed and no traceability of these locations, is to be kept as this has no technical value.
QA | QA | QAS1 | RCA not for every NC | Request RCA for each NC's, No more deviation request to client ! because this is deviation to ISO 9001), Project NCR's -> If specifically requested by the client follow detail RCA process ! 8D, 5 Why etc) ., ->If not keep simple and use NCR report template ! 1 text box) | Silver | Group QHSE | If in ER | 10 hrs /NCR in case detail RCA requested !e.g: 8D, 5 Why) .-> Considering meetings and involvement multiple parties etc. | N/A | If not specified by the client, keep it simple. If explicitly mentioned, no challanged, add additional cost impact. |  | Increase in workload, 00More comments from the client, 00Insufficient RCA's ( e.g linking root causes always with, human mistakes) |  | If in ER,10 hrs /NCR in case detail RCA requested !e.g: 8D, 5 Why) .-> Considering meetings and involvement multiple parties etc.,N/A,If not specified by the client, keep it simple. If explicitly mentioned, no challanged, add additional cost impact.,Increase in workload, 00More comments from the client, 00Insufficient RCA's ( e.g linking root causes always with, human mistakes)
QA | QA | QAB2 | APQP4Wind | Client defines to follow APQP4 Wind system. Possible to implement but time consuming and costly. | Bronze | Group QHSE | If in ER | 1.st Project 1FTE Following projects 0,25 FTE | N/A | Keep it away as much as possible., If possible use leverage being sub-contractor of SIF. !this normally applies to main contractor), If unavoidable, consider additional cost |  | Introducing additional administrative works and new, proccesses. ! Paper works) Involvement of multiple disciplines, Loss of project due to non-compliance APQP4 Wind |  | If in ER,1.st Project 1FTE Following projects 0,25 FTE,N/A,Keep it away as much as possible., If possible use leverage being sub-contractor of SIF. !this normally applies to main contractor), If unavoidable, consider additional cost, Introducing additional administrative works and new, proccesses. ! Paper works) Involvement of multiple disciplines, Loss of project due to non-compliance APQP4 Wind
QA | QA | QAB1 | Projec Audits-Notification Period | Smulders will work based on the project audit plan which is expected to be prepared prior, to execution of the process. In this project audit plan all sub-contractor audits will be, defined including the timeline. Any strict requirement than mentioned in Standard SMU way would have impact in planning/personal availability | Bronze | Group QHSE | If in ER | N/A | Tight audit schedule would lead to, delay on start of project project at sub-, contractor facilities. | Standart Proposal For Subctontractors, Check the requirements - 10-15 days, Notification: Western EU !Benelux) 3-5 days, Outside of Benelux - 10-15 days, Outside of Europe - 30 days | N/A | -Start production at sub-contractor facilities without audit -Receiving NCR from the client due to starting the project, before audit. |  | If in ER,N/A,Tight audit schedule would lead to, delay on start of project project at sub-, contractor facilities.,Standart Proposal For Subctontractors, Check the requirements - 10-15 days, Notification: Western EU !Benelux) 3-5 days, Outside of Benelux - 10-15 days, Outside of Europe - 30 days,N/A,-Start production at sub-contractor facilities without audit -Receiving NCR from the client due to starting the project, before audit.
Coating | Coating | CS9 | Stainless steel corrosion protection -, Loose items | All loose stainless steel items require a coating in order to have the same colour coding as, the areas around it or have anti-skid requirements., For anti-skid some projects require a painted anti-skid surface which is costly and time, consuming with a lot of discussion on the required finished quality: blasting of the surface,, sharp edges around bolt holes,... | Silver | Coating Surface Treatment Department |  | N/A | Tendererlders will follow the standards, and additionally blast all SS-parts by, inert grid before welding. ! Cost Impact, ), In order to protect them from any, contamination before/during/after, welding, a single coating layer will be, applied till safe distance from the, welding edge., There is an exception when parts are, to small and impossible to be coated, due to hot, temperatures !related to welding, and/or preheating), which, Tendererlders might cover as optimal, as practical possible, these parts will, be optimal protected from, contamination as far as, welding accessibility and process will, allow., These parts will be protected from, metallic grid blasting and will be, cleaned before getting a, full paint system, similar to the Carbon, Steel corrosion protection system that, they are welded onto., In this case, Tendererlders still highly, recommends to apply a full coating, system to the SS parts, as, due to, offshore application of stainless steel, | Powder coating to be established for hinges etc.. or stickers for anti-skid | Hinges from stainless steel are powder coated on, several projects !25380, 25360)., Grating fixation clamps with stickers on several, projects (25370, ..) | Small items which need coating and inert blasting. |  | N/A,Tendererlders will follow the standards, and additionally blast all SS-parts by, inert grid before welding. ! Cost Impact, ), In order to protect them from any, contamination before/during/after, welding, a single coating layer will be, applied till safe distance from the, welding edge., There is an exception when parts are, to small and impossible to be coated, due to hot, temperatures !related to welding, and/or preheating), which, Tendererlders might cover as optimal, as practical possible, these parts will, be optimal protected from, contamination as far as, welding accessibility and process will, allow., These parts will be protected from, metallic grid blasting and will be, cleaned before getting a, full paint system, similar to the Carbon, Steel corrosion protection system that, they are welded onto., In this case, Tendererlders still highly, recommends to apply a full coating, system to the SS parts, as, due to, offshore application of stainless steel,,Powder coating to be established for hinges etc.. or stickers for anti-skid,Hinges from stainless steel are powder coated on, several projects !25380, 25360)., Grating fixation clamps with stickers on several, projects (25370, ..),Small items which need coating and inert blasting.
Coating | Coating | CS8 | Coating systems |  | silver | Coating Surface Treatment Department | If in ER | When the client requires a Zn-Rich primer on an industrial, application:, 0 Involve the client in meetings with the CPREx team !, There are a lot of technical aspects and track records to, convince the client !, Zn ! first layer ) is 40% more expensive then other systems., Risks if Tendererlders has to use a Zinc Rich Primer:, Massive rework ! = mostly re-blasting ), Planning ! loss of time in case of rework as the blast hall will be, occupied again ), All suggested systems can be backed up by, - an extensive track record in offshore wind, - pre-qualification certificates including CP test - Datasheets and MSDS, The system as offered complies with the requirements in the, specified zone., Recommended alternative systems: see next slide | see impact cost | Tendererlders tries to avoid Zn-rich primers, and prefers above all long-track record Tendererlders Standard coating systems., Zinc primers are extremely difficult in serial manufacturing, and would increase prices:, - extreme tight tolerances on film thickness: 80 - 150 p ( min 64p, max 150p ), There is a risk on reaching too high thickness, which results in grinding repairs., On secundary steel or corners this is critical (corners, edges, .. ), - Ethyl Zinc-rich primer on friction areas requires humidity to cure., - Under- and Over-application needs to be blasted off due to stresses in the coating and cohesion failure., - Potential for cracking in corners and welds due to high thickness, There are currently systems in the market which provide equal corrosion resistance and therefore a deviation might be required, e.g.:, Glass Flake systems such as IZ-954-GF (despite the process related difficulties ( wear out pumps, .. ), High solids !aluminium) pigmented epoxy systems with proven track records | Examples:, - 3 OTM's vfor Morey East 17810-820-830 acc to, Siemens spec. 0 1ste layer with zinc rich primer 0, with a lot of corrections !extra sanding and, rework) on 1st layer, - At OTM for HKN 18000 also a zinc rich primer, was requested but after several meetings and, discussies the primer was replaced by glass flake -, Interzone 954GF with 10% glass flake, - Darmstadt bridge 18090 the 1ste layer was with, zinc, but required extra training and attention., The result was OK, but also thanks to the many, large straight surfaces., Extra information, Norsok M501 (rev6) pre-qualification certificates, including CP test, Long term track records, - Data for 4200h cycle test can be provided, this, reference is based on ISO12944 Part 9 - CX, environment | Alternative paint systems for the following zones !, atmospheric-corrosivity categories ):, C4/C5 systems !EN ISO 12944), Intershield 300 paint system !topsides), Interzone 954 paint system (TP's - jackets), CX systems !EN ISO 12944), Intershield 300 paint system !topsides), Interzone 954 paint system (TP's - immersed - splash -, atmospheric), Interzone 954GF !Glassflake) with 10% GF, despite the, process related difficulties ! wear out pumps ), Im4 systems !immersed with cathodic protection) !EN ISO, 12944), Interzone 954 paint system (immersed - splash -, atmospheric), Interzone 954GF !Glassflake) with 10% GF, despite the, process related difficulties ! wear out pumps) | N/A | If in ER,When the client requires a Zn-Rich primer on an industrial, application:, 0 Involve the client in meetings with the CPREx team !, There are a lot of technical aspects and track records to, convince the client !, Zn ! first layer ) is 40% more expensive then other systems., Risks if Tendererlders has to use a Zinc Rich Primer:, Massive rework ! = mostly re-blasting ), Planning ! loss of time in case of rework as the blast hall will be, occupied again ), All suggested systems can be backed up by, - an extensive track record in offshore wind, - pre-qualification certificates including CP test - Datasheets and MSDS, The system as offered complies with the requirements in the, specified zone., Recommended alternative systems: see next slide,N/A,see impact cost,Tendererlders tries to avoid Zn-rich primers, and prefers above all long-track record Tendererlders Standard coating systems., Zinc primers are extremely difficult in serial manufacturing, and would increase prices:, - extreme tight tolerances on film thickness: 80 - 150 p ( min 64p, max 150p ), There is a risk on reaching too high thickness, which results in grinding repairs., On secundary steel or corners this is critical (corners, edges, .. ), - Ethyl Zinc-rich primer on friction areas requires humidity to cure., - Under- and Over-application needs to be blasted off due to stresses in the coating and cohesion failure., - Potential for cracking in corners and welds due to high thickness, There are currently systems in the market which provide equal corrosion resistance and therefore a deviation might be required, e.g.:, Glass Flake systems such as IZ-954-GF (despite the process related difficulties ( wear out pumps, .. ), High solids !aluminium) pigmented epoxy systems with proven track records,Examples:, - 3 OTM's vfor Morey East 17810-820-830 acc to, Siemens spec. 0 1ste layer with zinc rich primer 0, with a lot of corrections !extra sanding and, rework) on 1st layer, - At OTM for HKN 18000 also a zinc rich primer, was requested but after several meetings and, discussies the primer was replaced by glass flake -, Interzone 954GF with 10% glass flake, - Darmstadt bridge 18090 the 1ste layer was with, zinc, but required extra training and attention., The result was OK, but also thanks to the many, large straight surfaces., Extra information, Norsok M501 (rev6) pre-qualification certificates, including CP test, Long term track records, - Data for 4200h cycle test can be provided, this, reference is based on ISO12944 Part 9 - CX, environment,Alternative paint systems for the following zones !, atmospheric-corrosivity categories ):, C4/C5 systems !EN ISO 12944), Intershield 300 paint system !topsides), Interzone 954 paint system (TP's - jackets), CX systems !EN ISO 12944), Intershield 300 paint system !topsides), Interzone 954 paint system (TP's - immersed - splash -, atmospheric), Interzone 954GF !Glassflake) with 10% GF, despite the, process related difficulties ! wear out pumps ), Im4 systems !immersed with cathodic protection) !EN ISO, 12944), Interzone 954 paint system (immersed - splash -, atmospheric), Interzone 954GF !Glassflake) with 10% GF, despite the, process related difficulties ! wear out pumps)
Coating | Coating | CS7 | Acceptance criteria for coating layers | EN ISO 12944, NORSOK M-501, VGB/BAW-Standard, EN 1090-2, DNVGL-OS-C401, ISO 19840, Huge number of related standards !, The standards define as requirement on coating :, 1) A minimum number of coatings !MNOC) often depending on the coating type !EP, PU,, Zinc Primers, ..), 2) A minimum DFT for the complete system !sometimes also for primer), 3) Max. DFT in relation to the NDFT !i,.e. 3 x NDFT acc. ISO 12944), 4) Probably a special certification of the coating system !always for offshore coatings) | silver | Coating Surface Treatment Department | If in ER | see clarification / risk | see clarification / risk | In general max. and min. DFT are technical and material specific values with no relation to project specific NDFTs., For materials often used by Tendererlders we have already received a list from International Paint regarding these values !s. R-TI-GR-317)., As long as the same kind of binder is used for the next layer:, All low (< 80% or rather 90% of NDFT) and high DFT's (> 2,5 x NDFT) are marked during inspection., Only areas with values outside the specified limits acc. R-TI-GR-317 are reworked by touch up or sanding !also in combination with a touch up), All other low and high values are compensated with the next layer., As for every touch up the min. overcoating time !several hours !) has to be respected before application of next layer this approach leads to a significant, safe of time and costs without affecting quality and/or the functionality of the corrosion protection system. | N/A | If every layer needs to be touched up according to min and, max DFT, this has a significant cost impact and time impact,, with very limited and potentially contra-productive added, value., 80/20 or even 90/10 Rule can be accepted, but in, combination with :, As long as the same kind of binder is used for the next, layer:, All low (< 80% or rather 90% of NDFT) and high DFT's (> 2,5 x, NDFT) are marked during inspection., Only areas with values outside the specified limits acc. R-TI-, GR-317 are reworked by touch up or sanding !also in, combination with a touch up), All other low and high values are compensated with the next, layer., 90/10-rule shall be avoided. 90/10 Leads to additional, rework without any benefit regarding quality. Argument:, ISO 19840 only defines 80/20-rule as a possible but not, mandatory guideline., Additional Remarks, - This topic shall be discussed for every tender even if not, explicitly mentioned in client's specifications., - 90/10-rule shall be avoided. Leads to additional rework, without any benefit regarding quality. Also ISO 19840 only, defines 80/20-rule !just as an argument), - In practice PU-topcoat only checked visually regarding, closed layer, sufficient opacity and possible defects. An, additional DFT check technically makes no sense., - There are special requirements regarding DFT measuring | N/A | If in ER,see clarification / risk,N/A,see clarification / risk,In general max. and min. DFT are technical and material specific values with no relation to project specific NDFTs., For materials often used by Tendererlders we have already received a list from International Paint regarding these values !s. R-TI-GR-317)., As long as the same kind of binder is used for the next layer:, All low (< 80% or rather 90% of NDFT) and high DFT's (> 2,5 x NDFT) are marked during inspection., Only areas with values outside the specified limits acc. R-TI-GR-317 are reworked by touch up or sanding !also in combination with a touch up), All other low and high values are compensated with the next layer., As for every touch up the min. overcoating time !several hours !) has to be respected before application of next layer this approach leads to a significant, safe of time and costs without affecting quality and/or the functionality of the corrosion protection system.,N/A,If every layer needs to be touched up according to min and, max DFT, this has a significant cost impact and time impact,, with very limited and potentially contra-productive added, value., 80/20 or even 90/10 Rule can be accepted, but in, combination with :, As long as the same kind of binder is used for the next, layer:, All low (< 80% or rather 90% of NDFT) and high DFT's (> 2,5 x, NDFT) are marked during inspection., Only areas with values outside the specified limits acc. R-TI-, GR-317 are reworked by touch up or sanding !also in, combination with a touch up), All other low and high values are compensated with the next, layer., 90/10-rule shall be avoided. 90/10 Leads to additional, rework without any benefit regarding quality. Argument:, ISO 19840 only defines 80/20-rule as a possible but not, mandatory guideline., Additional Remarks, - This topic shall be discussed for every tender even if not, explicitly mentioned in client's specifications., - 90/10-rule shall be avoided. Leads to additional rework, without any benefit regarding quality. Also ISO 19840 only, defines 80/20-rule !just as an argument), - In practice PU-topcoat only checked visually regarding, closed layer, sufficient opacity and possible defects. An, additional DFT check technically makes no sense., - There are special requirements regarding DFT measuring
Coating | Coating | CS6 | Time between blasting and coating | Coating standards describe the following requirements:, Norsok M-501:, "Paints and coating materials shall be applied to the abrasive blast cleaned surfaces before, any oxidation appears. Surfaces that show visible oxidation or deterioration shall be re-, blasted to the required grade." But no specific time limitation is indicated in the Standard., But no specific time limitation is indicated in the Standard., EN ISO 12944: No specific time limitation is described., VGB/BAW: The first coat of the coating system should be applied as soon as possible after blasting. | silver | Coating Surface Treatment Department | If in ER | see clarification / risk | see clarification / risk | For large constructions such as decks, TP's, etc, is the time frame limitation between blasting and the 1st coat as described in the VGB not feasible., A derogation shall always be requested when this requirement applies., Independent of the time between blasting and the application of the 1st coat, Tendererlders ensures the quality by checking the cleanliness of the blasted, Independent of the time between blasting and the application of the 1st coat, Tendererlders ensures the quality by checking the cleanliness of the blasted, surface just before !max 1 hour) applying the 1st coat !Stripe coat start process first coat). | Statement signed by International Paint:, https://intranet.Tendererlders.com/sites/IMS/IM, S%20Documents/R-TI-GR-104%20Statement%20-, %20surface%20preparation%20signed%20IP.PDF Statement signed by Hempel:, https://intranet.Tendererlders.com/sites/IMS/IM, S%20Documents/R-TI-GR-204%20Statement%20- %20surface%20preparation%20signed%20Hempel, %20surface%20preparation%20signed%20Hempel, .pdf | If the VGB is applicable and/or a short time limit is, requested by the customer ERs, Tendererlders shall always, request a derogation for this requirement, with the, following explanation:, For large constructions such as decks, TP's, etc, is the time, frame limitation between blasting and the 1st coat not, feasible., The most important factor is the resulting cleanliness of the, surface !e.g.Sa 2,5 or Sa3) at the start of the first coat., Independent of the time between blasting and the, application of the 1st coat, or the relative humidity,, Tendererlders ensures the quality by checking the, cleanliness of the blasted surface just before applying the, 1st coat !max 1 hour)., Tendererlders guarantees that under no circumstances are, coatings applied to cleaned surfaces that show signs of fresh, rust and/or contamination, including condensation. In such, situations, the workpiece must be reblasted to achieve the, required level of surface cleanliness., If blasting and coating in compartments would be done, this, goes with a Cost impact | N/A | If in ER,see clarification / risk,N/A,see clarification / risk,For large constructions such as decks, TP's, etc, is the time frame limitation between blasting and the 1st coat as described in the VGB not feasible., A derogation shall always be requested when this requirement applies., Independent of the time between blasting and the application of the 1st coat, Tendererlders ensures the quality by checking the cleanliness of the blasted, Independent of the time between blasting and the application of the 1st coat, Tendererlders ensures the quality by checking the cleanliness of the blasted, surface just before !max 1 hour) applying the 1st coat !Stripe coat start process first coat).,Statement signed by International Paint:, https://intranet.Tendererlders.com/sites/IMS/IM, S%20Documents/R-TI-GR-104%20Statement%20-, %20surface%20preparation%20signed%20IP.PDF Statement signed by Hempel:, https://intranet.Tendererlders.com/sites/IMS/IM, S%20Documents/R-TI-GR-204%20Statement%20- %20surface%20preparation%20signed%20Hempel, %20surface%20preparation%20signed%20Hempel, .pdf,If the VGB is applicable and/or a short time limit is, requested by the customer ERs, Tendererlders shall always, request a derogation for this requirement, with the, following explanation:, For large constructions such as decks, TP's, etc, is the time, frame limitation between blasting and the 1st coat not, feasible., The most important factor is the resulting cleanliness of the, surface !e.g.Sa 2,5 or Sa3) at the start of the first coat., Independent of the time between blasting and the, application of the 1st coat, or the relative humidity,, Tendererlders ensures the quality by checking the, cleanliness of the blasted surface just before applying the, 1st coat !max 1 hour)., Tendererlders guarantees that under no circumstances are, coatings applied to cleaned surfaces that show signs of fresh, rust and/or contamination, including condensation. In such, situations, the workpiece must be reblasted to achieve the, required level of surface cleanliness., If blasting and coating in compartments would be done, this, goes with a Cost impact
Coating | Coating | CS5 | Relative humidity during blasting and coating | Norsok M501 Section 4.4 states:, No final blast cleaning or coating application shall be done if the relative humidity is more, than 85 % and when the steel temperature is less than 3 °C above the dew point. Coating, shall only be applied or cured at ambient and steel temperatures above 0 °C., VGB-S-021-03-2018-04 Section 3 for surface preparation states the following:, During blast cleaning work the following climatic conditions shall be observed:, Ambient and object temperature > +10 °C and < +30 °C, Relative humidity < 60 % up to the completion of application of the first coating film;, thereafter < 80 %, Dewpoint distance >3 K !Verification by continuous measurement of ambient temperature, and humidity, and object temperature must be checked by individual measurements, at, least every 3 hours) | silver | Technology-department Coating Surface Treatment Department | If in ER | see clarification / risk | see clarification / risk | Tendererlders complies with the conditions defined by Norsok., The product data sheet of the paint manufacture shall be taken as minimum requirement. | N/A | If the client insist on complying with the VGB standards, Tendererlders reply:, Tendererlders complies with the conditions defined by the, Norsok requirements, If the client insists on following the VGB standard ! which, Tendererlders considers as extra requirement ),, Tendererlders can not comply within own facilities unless, Tendererlders rents additional equipment, such as, dehumidifiers and additional heating and extraction, equipment. Following VGB would require for touch up !, Outside ) building scaffolding, tents, and installing heating., Those come with an additional cost and time impact !, deviation required )., Tendererlders CPREx request for a meeting to go in detail,, case by case., Recommended to define in tender:, The time between blasting and coating is not to be limited,, but the service conditions are to be controlled before, coating according to the Norsok M-501, The product data sheet of the paint manufacture shall be, taken as minimum requirement | N/A | If in ER,see clarification / risk,N/A,see clarification / risk,Tendererlders complies with the conditions defined by Norsok., The product data sheet of the paint manufacture shall be taken as minimum requirement.,N/A,If the client insist on complying with the VGB standards, Tendererlders reply:, Tendererlders complies with the conditions defined by the, Norsok requirements, If the client insists on following the VGB standard ! which, Tendererlders considers as extra requirement ),, Tendererlders can not comply within own facilities unless, Tendererlders rents additional equipment, such as, dehumidifiers and additional heating and extraction, equipment. Following VGB would require for touch up !, Outside ) building scaffolding, tents, and installing heating., Those come with an additional cost and time impact !, deviation required )., Tendererlders CPREx request for a meeting to go in detail,, case by case., Recommended to define in tender:, The time between blasting and coating is not to be limited,, but the service conditions are to be controlled before, coating according to the Norsok M-501, The product data sheet of the paint manufacture shall be, taken as minimum requirement
Coating | Coating | CS4 | P2/P3 Requirements | DNVGL-RP-0416 | silver | Technology-department, Coating Surface Treatment Department | If in ER | If the client requires an P3 surface smoothness on points 1.2 and, 1.3, Weld ripple/profile P3: fully dressed/smooth ?, Tenderer can agree to change towards P3, with cost impact of :, - Substation: 2 €/ton, - Jacket: 30 minutes extra work-charge per running weld-meter, If the client requires an additional, P3 surface smoothness on points 3.6, Tenderer can not accept to change towards P3 on 3.2-3.3-, 3.4.3.5.36, If the client insists, a detailed cost impact investigation and, feasibility study is to be done in cooperation with Production. | see impact cost | Tendererlders way is to agree on what is achievable in the field., Tendererlders way is to agree on what is achievable in the field. We refer to the table in the DNVGL-RP-0416, 6.2.1. | N/A | see impact cost/planning | N/A | If in ER,If the client requires an P3 surface smoothness on points 1.2 and, 1.3, Weld ripple/profile P3: fully dressed/smooth ?, Tenderer can agree to change towards P3, with cost impact of :, - Substation: 2 €/ton, - Jacket: 30 minutes extra work-charge per running weld-meter, If the client requires an additional, P3 surface smoothness on points 3.6, Tenderer can not accept to change towards P3 on 3.2-3.3-, 3.4.3.5.36, If the client insists, a detailed cost impact investigation and, feasibility study is to be done in cooperation with Production.,N/A,see impact cost,Tendererlders way is to agree on what is achievable in the field., Tendererlders way is to agree on what is achievable in the field. We refer to the table in the DNVGL-RP-0416, 6.2.1.,N/A,see impact cost/planning